## Title Sheet
4PEX Ltd. | Release 2 | 0.1 | 0.1 | 2014-08-01 14:50
`
Version: 0.1
Trianz | HighRadius
GCP to Azure Project Migration
Migration Planning Runbook

## ToC (hidden)
Table of Contents
Equinix
Data Centre Migration Runbook
Glossary
Approval
Contacts
CI In-scope
Migration-AWS
Post-Migration-AWS
Rollback Plan
RACI
Pre Migration - AWS
Infra Firewall Change

## Milestone Summary (hidden)
TOC
Version: 0.1
Application Migration Milestone Summary
| Milestone/Due Date | T - plan(due date) for Small application | T - plan(due date) for Medium application | T - plan(due date) for Large application | T - plan(due date) for Extra Large application | Only working days considered for t- plan
| Assessment Start | 50 | 60 | 70 | 80
| Application Assessment sign-off | 40 | 45 | 55 | 65
| App Subscription done and shared | 35 | 50 | 60 | 70
| FCR Request submission | 30 | 35 | 45 | 55
| Runbook sign-off | 30 | 35 | 45 | 55
| Change request submitted | 15 | 20 | 30 | 40
| FCR Execution (incl test) | 10 | 15 | 20 | 25
| Initial Sync (Live copy)* | 5 | 10 | 15 | 20 | *will vary as per data size and scheduling
| Pre-migration Go no Go | 1 | 1 | 1 | 1
| Migration cutover | T | T | T | T
| UAT Sign -off | + 2 Days | + 2 Days | + 2 Days | + 2 Days
| Hyper care Signoff | + 10 Days | + 10 Days | + 10 Days | + 10 Days
Application size calculation
| weightage | 1 | 2 | 3 | 4 | 5
| 1. Volume of data to be migrated (GB) | <=500 | 500 - 2048 | 2048 - 5120 | 5120 - 10240 | >10240
| 2. # of interfaces to other apps/processes, | <=5 | 5-10 | 10-15 | 15-20 | >20
| 3. # of servers or ApplicationTier (1, 2 or 3) | <=5 | 5-10 | 10-20 | 20-30 | >30
| 4. # affected users | <=50 | 50-500 | 500-1000 | 1000-2000 | >2000
|  | Application Criteria Score (sum of weightage) |  |  | Sum of Application Criteria Score
| 1. Volume of data to be migrated | 2 |  | S | <=6
| 2. # of interfaces to other apps/processes, | 1 |  | M | 6-10
| 3. # of servers | 1 |  | L | 10-15
| 4. # affected users | 1 |  | XL | >15
| Total Complexity Score | 5
| Application complexity | MEDIUM |  |  |  |  | Small

## Change Approvals
Migration Planning Runbook
CR # | Date Raised | System/ Remarks
TBD | TBD | TBD

## Pre-Migration-MPC (hidden)
TOC
# | Status | Owner(s) | Task Description | Server(s)/Systems(s) | Due Date | T-Minus (days) | Start Time* | End Time* | Duration | Dependencies
Administrative
1 |  | Wipro/ E.ON/ E.ON / Application Team | Final confirmation of MG's/applications/Servers in scope for this migration | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
2 |  | Wipro/ E.ON/ E.ON / Application Team | Agree migration schedule, downtime and resource requirement with relevant stakeholders | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
3 |  | Application Team | EON Internal audit process-Application manager to confirm completion of Cloud Readiness Assessment as per mandatory requirement by EON Audit Requirement for Private Cloud | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
4 |  | Application Team | General requirement for all BIT Area--Application manager to confirm Security exception approval if applicable, from EON Security Team (Update Move Event Sheet) | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
5 |  | Application Team | Application Manager to confirm As-Is environment fulfils the E.ON Security Requirements. In case not, the Application Manager need to raise security exception for the target landing zone. | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
6 |  | Wipro PMO Team | Raise a Change Request for Server Move group starting from pre migration till cut over (Update Move Event Sheet) | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
7 |  | Application Team | Approve Change Request in Service Now (Update Move Event Sheet) | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
8 |  | EON EDT Team | Send communication to EON End users reg migration schedule and downtime | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
9 |  | EON EDT Team | Ensure communication is set to Third party/Vendors (as applicable) | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
Pre Migration Tasks - Server and Storage
10 |  | Wipro Migration team | Create a 'WiproAdmin' local admin account and password and share these (For Windows Server) | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
11 |  | Wipro Migration Team | Verify creation of appropriate port groups at Target vCenter for respective vLANs | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
12 |  | Wipro Migration Team | Save all the Eventlogs on the common shared location on the SharePoint | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
13 |  | Wipro Migration Team | Export the list of services and save it on common shared location on the SharePoint | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
14 |  | Wipro Migration Team | Execute Ipconfig/all from CLI and save it on common shared location on the SharePoint | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
15 |  | Wipro Migration Team | Execute route print from CLI and save it on common shared location on the SharePoint | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
16 |  | Wipro Migration Team | Verify any network shares which are configured, capture the screenshot and save it on common shared location on the SharePoint | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
17 |  | Wipro Migration Team | VM target hosts / Cluster identified - Refer LZ Details | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
18 |  | Wipro Migration Team | Check and unmount CDROM / ISO drive from virtual servers | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
19 |  | Wipro Migration Team | Create required Storage LUNs at target storage -- Refer LZ Details | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
Network and Security Task(s)
20 |  | Wipro Network Team | Ensure purticular VLAN is extended to Target ( Mandatory to have this done - Wipro and E.ON ) | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
21 |  | Wipro Network Team | Identify External (Public) IP & DNS requirements | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
22 |  | Wipro Network Team | Ensure Load balancer configuration is in-place at Target Infrastructure | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
23 |  | Wipro Network Team | Confirm routing and reachablility from E.ON Load balancers to Wipro LB members and vice versa. | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
Backup
24 |  | Wipro Backup Team | Ensure the backup is working and corresponding backup jobs are successful | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
25 |  | Wipro Backup Team | Hostname of the backup NIC to be registered in wiprodc.local domain | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC
Systems Health check
26 |  | Wipro BAU | Perform Server Health Checks and Share the Status - Inform about any open/existing Alerts / Incidents that have not been resolved both from an OS and hardware perspective. E.g. Server Disk Space, Memory/ CPU Utilization etc | CI Sheet | TBC | TBC | TBC | TBC | TBC | TBC

## Blockers
Application | Blocker's | Owner | Owner Name | Trainz Owner Name | Status
AccelQ | Stagging server requires datastore to support migration SMB- 1650 GB ((Currently we have 7TB configured for NFS, that can be split with NFS - 4 TB & SMB 3 TB)
AccelQ | SMB to be configured in Staging server - Not applicable ifl VM's are Linux based
AccelQ | Stagging Server to Source VM (Linux) Port 2049 need to whitelisted Cmigrate to Source VM Port 22 need to whitelisted
AccelQ | Dedicated Host Configuration Readiness
AccelQ | Onboard Target Azure account in Concierto
AccelQ | Stagging Server to Source VM (Linux) Port 2049 need to whitelisted Cmigrate (IP address) to Source VM Port 22 need to whitelisted

## Pre-Migration-Project
# | Status | Section | Owner(s) | Task Description | Applicable servers | Start Date | End Date | Comments / Dependency | Stakeholder/Contacts | Process Reference + Documentation
1 |  | Pre-Requisites |  | Stagging Server - GCS staging server is configured with required privileges and SSH key access - For Discovery and assesment need 200 GB on root file system For migration we need to configure NFS and SMB share as per the data size on Linux and Windows Servers Stagging Sever IP:
2 |  | Pre-Requisites |  | Enable Packages in Staging Server - Python (≥ 3.6zlib packeges), boto3 (≥ 1.18.0), botocore (≥ 1.21.0), Terraform, AWS CLI, NFS and Samba configuration, NMAP, qemu-img, jq, nfs-utils, rpcbind, lvm2, libselinux-python3, rpm, unzip, wget, and dnf AWS CLI installation in staging server- /usr/local/bin/ Url AWS CLI: https://docs.aws.amazon.com/cli/latest/userguide/getting-started-install.html#getting-started-install-instructions Terraform Url: https://www.terraform.io/downloads
3 |  | Pre-Requisites |  | "Storage Gateway Security Group Configuration: VPC-level / Outbound: All traffic allowed Inbound Rules: All traffic / Source: VPC CIDR range"
4 |  | Pre-Requisites |  | Whiitelist the following domains on staging server if internet is not enabled : *.registry.terraform.io *.hashicorp.com *.amazon.com
5 |  | Pre-Requisites |  | Enable Network Connectivity Staging Server to Windows Servers On-Prem over 5986 Windows Source On-Prem Servers to Staging Server On-Prem over 445 for SMB Concierto in AWS to Source Windows Servers On-Prem over 5986 Network bandwidth (VPN / Direct connect) 1. On-prem to Target AWS Account 2. On-prem to C-migrate platform 3. Target AWS ccount to Cmigrate platform
6 |  | Pre-Requisites |  | For Windows Server: - 1. Required packages: PowerShell 3.0 or later, .NET 4.0 or later 2. WinRM service must be running 3. Enable WinRM secured port listener on port 5986 4. Source: (https://learn.microsoft.com/en us/troubleshoot/windows-client/system-management components/configure-winrm-for-https) 5. TLS 1.2 or higher must be enabled on all Windows workloads 6. PowerShell execution policy should be set to "remote signed" on Windows Workloads 7. Disk Requirements (Windows) Each disk (OS and Data disk) must have at least 13% of free disk space available.
8 |  | Pre-Requisites (Migration) |  | Windows Local user with Admin privileges required for migration (Migration will not work with Domain user )-NOT Required as this app has Windows servers
9 |  | Pre-Requisites (Migration) |  | Server uptime should be less than 30-45 days
10 |  | Pre-Requisites (Migration) |  | Identify Source VM-to- Target subnet mapping for pilot server migration in Target Env
11 |  | Pre-Requisites (Migration) |  | Create specific Security Groups for target Linux VMs Linux SG ports (22,443,2049)
12 |  | Pre-Requisites (Migration) One time activity for each account | Trianz | Create 2 S3 or GCS Bucket one for SMB and another for NFS, Storage gateway appliances, Storage gateway interface endpoint and S3 or GCS interface endpoint. Activate the storage gateway and configure the SMB and NFS shares Create a C-Migrate user with IAM roles and permissions (Programatic access only)
13 |  | Pre-Requisites (Migration) One time activity for each account | Trianz | Onboard the target account to the Concierto platform

## Migration-Project
# | Status | Section | Owner(s) | Task Description | Applicable servers | Start Date | End Date | Duration(Mins) | Dependencies | Notes
1 |  | Discovery & Assessment | Trianz | From Concertio Migrate Perform Host-IP and file based discovery for all VMs
2 |  |  | Trianz | Create an Assessment report Environment
3 |  | Migration | Trianz | Verify the Approved generated Assessment report to create Plan ID
4 |  |  | Trianz | Group applications/servers into structured migration waves for phased execution.
5 |  |  |  | Idetify dedicated host Resource group
6 |  |  | Trianz | Define Landing Zone for Workloads - VPC, Subnet, S3 Bucket, S3 Secuirty group, transit type
7 |  |  | Trianz | Define VM build templates including instance type, keypair & availability zone, instance taging, encryption, IMDS V2, disk type.
8 |  |  | Trianz | Group servers logically (OS/application/Env based) for simultaneous migration.
9 |  |  | Trianz | Map each move group to its target cloud configuration.
10 |  |  | Trianz | Share migration plan for review and secure change approval.
11 |  |  | Trianz | CAB approval validates and approves plan for execution.
12 |  |  | Trianz | Ensure on-prem servers are running before starting replication/migration.
13 |  |  | Trianz | Trigger migration execution via CMigrate platform.
14 |  |  | Trianz | Monitor backup, template creation, provisioning, restore & status logs.
15 |  |  | Trianz | Confirm EC2/VMs created successfully in target cloud.
16 |  |  | Trianz | Sanity check validations for the migrated VM's and handover to application team to validate

## Migration-MPC (hidden)
TOC
# | Status | Owner(s) | Task Description | Server(s) | Start Time* | End Time* | Duration(Mins) | Dependencies | Notes
First Check
1 |  | Wipro Backup Team | Verify and ensure the incremental backup is successful | CI Sheet | 2021-09-29 08:00 | 2021-09-29 08:10 | 10
2 |  | Wipro BAU/ Migration Team | Perform Server Health Checks and Share the Status - Ensure that there are no open/existing Alerts / Incidents that have not been resolved both from an OS and hardware perspective. E.g. Server Disk Space, Memory/ CPU Utilization etc | CI Sheet | 2021-09-29 08:10 | 2021-09-29 08:20 | 10
3 |  | Wipro Tools Team | Suppress monitoring alert / disable monitoring | CI Sheet | 2021-09-29 08:20 | 2021-09-29 08:30 | 10
4 |  | Wipro Migration team | Log in to server & verify the access | CI Sheet | 2021-09-29 08:30 | 2021-09-29 08:40 | 10
Go/No Go Meeting
5 |  | Wipro | Ensure all key Members are available and ready for the Migration. | CI Sheet | 2021-09-29 08:40 | 2021-09-29 08:45 | 5
6 |  | Wipro/E.ON/EDT | Wipro/E.ON Migration leads announces start of migration | CI Sheet | 2021-09-29 08:45 | 2021-09-29 08:50 | 5
Server Task(s) - T Day (Outage Windows Starts from here)
7 |  | Wipro BAU/ Migration Team | Stop the scheduled tasks - Local OS | CI Sheet | 2021-09-29 08:50 | 2021-09-29 09:00 | 10
8 |  | Application Team | Stop the application services at Source and make it as a Manual. (Sub-Tasks to be taken from App Owners) - Keep it in maintainance mode | CI Sheet | 2021-09-29 09:00 | 2021-09-29 09:10 | 10
9 |  | Wipro Migration team | Take the VM Snapshot | CI Sheet | 2021-09-29 09:10 | 2021-09-29 09:20 | 10
10 |  | Wipro Migration team | Perform V2V Final Sync (Data Copy) via vSphere Replication | CI Sheet | 2021-09-29 09:20 | 2021-09-29 09:40 | 20
11 |  | Wipro Migration team | Monitor / Verify the Final Sync for Completion | CI Sheet | 2021-09-29 09:40 | 2021-09-29 09:45 | 5
12 |  |  | Verify Source VM Shutdown | CI Sheet | 2021-09-29 09:45 | 2021-09-29 09:50 | 5
13 |  | Wipro Migration team | Move the Target VM on the required Datastore and Host Cluster | CI Sheet | 2021-09-29 09:50 | 2021-09-29 10:00 | 10
14 |  | Wipro Migration team | Verify Production and Mgmt Network on target VM - attach the designated Port Group. | CI Sheet | 2021-09-29 10:00 | 2021-09-29 10:05 | 5
15 |  | Wipro Migration team | Verify target VM Power Status | CI Sheet | 2021-09-29 10:05 | 2021-09-29 10:15 | 10
16 |  | Wipro Migration team | Verify VM time synchronized to NTP time | CI Sheet | 2021-09-29 10:15 | 2021-09-29 10:25 | 10
17 |  | Wipro Migration team | Verify event log for any errors | CI Sheet | 2021-09-29 10:25 | 2021-09-29 10:35 | 10
18 |  | Wipro Migration team | Verify Domain Name Resolution and Reachability | CI Sheet | 2021-09-29 10:35 | 2021-09-29 10:45 | 10
19 |  | Wipro Migration team | Check all automatic OS services are running correctly. | CI Sheet | 2021-09-29 10:45 | 2021-09-29 10:55 | 10
20 |  | Application Team / Wipro DBA | Start DB Service & application services , Also change the services to Automatic start which were set to Manual before Migration | CI Sheet | 2021-09-29 10:55 | 2021-09-29 11:05 | 10
21 |  | Application Team / E.ON | Validate all the Virtual IPs and names post migration and their accessibility from respective end-points. | CI Sheet | 2021-09-29 11:05 | 2021-09-29 11:15 | 10
22 |  | Application Teams | Perfrom initial post-migration pre go live application tests-that have been agreed during early L3 planning with BIT test manager. A number of use test cases will be run, result recorded and also timing to complete the tests . This baselined time will be used post migration to compare the performance between Source and Target system. | CI Sheet | 2021-09-29 11:15 | 2021-09-29 12:15 | 60
23 |  | Application Team / E.ON/ Wipro/BIT Manager | Go-No/Go decision- Actual time will be detailed during L3 planning. In general the time required to complete the roll back to ensure the system is back in original BAU state | CI Sheet | 2021-09-29 12:15 | 2021-09-29 12:25 | 10
24 |  | Wipro Tools Team | Installation & configuration of backup, AV, JetPatch & Monitoring tools | CI Sheet | 2021-09-29 12:25 | 2021-09-29 12:35 | 10
25 |  | Wipro Tools Team | Check and resume for any scheduled jobs configured on Ctrl-M / UC4 | CI Sheet | 2021-09-29 12:35 | 2021-09-29 12:45 | 10
26 |  | Wipro Migration team | Check and resume for any scheduled jobs configured on OS | CI Sheet | 2021-09-29 12:45 | 2021-09-29 12:55 | 10
Formulas:
End Time* = ([Start Time*]+[Duration(Mins)]/1440)
Start Time* = [End Time*, row above]

## Post-Migration-Project
# | Status | Owner(s) | Phase | OS Name | Task Description | Start Time* | End Time* | Duration(Mins) | Notes | Dependencies
1 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | Validate VPC/Subnets/SG of target server ( N/W validation)
2 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | Validate the connectivity of migrated VMs in target account.
3 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | Rename the server as per AWS naming convention and add the the server into the domain
4 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | Install Adot monitoring agent and configure on the migrated VMs
5 | NA | Trianz Migration Team | Post Migration Task | Linux/Windows | Install EC2 Serial Console for Production VMs
6 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | Install SSM agent in all VMs
7 | NA | Trianz Migration Team | Post Migration Task | Linux/Windows | Install Elastic DR agent on all Production VMs
8 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | BESclient- BigFix Agent Restart/Reinstall all VMs
9 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | Nessus Agent-Stop the Agent / Remove the machine id / start the Agent For New build Nessus Agent need to be installed
10 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | CrowdStrike Falcon Sensor-Stop the current service & Remove the existing version
11 |  | HiR | Post Migration Task | Linux/Windows | Inform to Anderson/Suresh to add the servers in the respertive OU
12 |  | Trianz Migration Team | Post Migration Task | Linux/Windows | Create the Application specific SG with required application specific rules.
13 | NA | Trianz | Post Migration Task | Linux/Windows | Reach out to App Owners to collect the Pool Ips for F5 additions if any to add ICMP traffic in AWS SG.
14 | NA | Trianz N/W Team | Post Migration Task | Linux/Windows | Send out an update to Peter and team to add the URL with node and Pool info 2 weeks in advance.
15 |  | HiR | Post Migration Task | Linux/Windows | Release the server to Application team and have them Verify
16 |  | HiR | Post Migration Task | Linux/Windows | App team to perform the application configurations like Property files ,http.conif , jdbc.properties and Key, trust store
17 |  | HiR | Post Migration Task | Linux/Windows | Dependencies Validation Check integrations with other systems/appsfor middleware configuration
18 |  | HiR | Post Migration Task | Linux/Windows | Enable Firewall to allow Traffic for Boomi component

## Pre Cutover Tasks - Project
# | Status | Owner(s) | Phase | OS Name | Task Description | Start Time* | End Time* | Duration(Mins) | Notes | Dependencies
1 |  | Trianz Migration | Pre-Cutover Task | Linux/Windows | Validate VPC/Subnets/SG of target server ( N/W validation)
2 |  | Trianz Migration Team | Pre-Cutover Task | Linux/Windows | Target Instance Tag Information Validation (Backup Tag validation if applicable)
3 |  | Application Team | Pre-Cutover Task | Linux/Windows | App team to perform the application Validations like Property files,http.conif , jdbc.properties and Key, trust store
4 |  | Trianz Migration Team/ SRE Tier2 | Pre-Cutover Task | Linux/Windows | BESclient - BigFix Agent Validation
5 |  | Trianz Migration Team/ SRE Tier3 | Pre-Cutover Task | Linux/Windows | Nessus Agent Validation
6 |  | Trianz Migration Team/ SRE Tier4 | Pre-Cutover Task | Linux/Windows | CrowdStrike Falcon Sensor-Validation
7 |  | Trianz Migration Team | Pre-Cutover Task | Linux/Windows | Validate SSm agent should be available on line in VMs
8 |  | Trianz Migration Team | Pre-Cutover Task | Linux | EFS mount volume validation in target instances if applicable
9 |  | Trianz Migration Team | Pre-Cutover Task | Linux/Windows | Install Adot monitoring scripts on the migrated VMs

## Cutover Tasks - Project
# | Status | Owner(s) | Phase | Indicator(All/Specific) | OS Name | Activities | Task Description | Expected Duration(Mins) | Start Time* | End Time* | Actual Duration(Mins) | Notes | Dependencies
1 |  | Trainz Migration Team | Change Window | All | Linux/Windows | Sequential-1 | Rename the host name in target as per source VM | 15 mins
2 |  | Trainz Migration Team | Change Window | All | Linux/Windows | Sequential-2 | Intiate the final delta sync (Not Cutover)- Considering incremental data of 2GB | 30 mins
3 |  | Trainz Migration Team | Change Window | All | Linux/Windows | Sequential-3 | Rename the target host name back to quinix naming standard(as previous target host name) and join the servers to domain | 20 mins
4 |  | App Team | Change Window | All | Linux/Windows | Parallel-1 | Disable the monitoring alerts On prem VMs if any synthetic monitoring for URL | 15 mins
5 |  | App Team | Change Window | Specific | Linux/Windows | Parallel-1 | Stop Extraction Jobs/schedule Jobs and clear middleware Queues on source VMs | 15 mins
6 |  | Backup Team | Change Window | Specific | Linux/Windows | Parallel-1 | Disable the Backup of respective VM On Perm | 15 mins
7 |  | DB Team | Cutover | Specific | Linux/Windows | Parallel-1 | Stop the DB and app services on Source VMs - Stop MsSql services, agent and SSIS services( 5 min Windows),Transaction logs backup for cluster and Always On( 30 mins Windows) Update Tablespace as read only, take final incremental backup, metadata backup( 30 mins - Oracle),Stop Httpd, Redis, Kafka, Elasticsearch and App servers from app side( 45 min) | 30 mins
8 |  | App Team | Cutover | All | Linux/Windows | Sequential-4 | Shutdown the source VMs | 5 mins
9 |  | Trainz/Linux Team | Cutover | Specific | Linux | Parallel-1 | Trigger AWS data sync(final delta sync) if App includes NFS filesystem - 30min interval for Delta | 30 mins
10 |  | App Team | Cutover | Specific | Linux/Windows | Parallel-1 | App services - Stop Httpd, Redis, Kafka, Elasticsearch and etc from app side( 20 mins) | 20 mins
11 |  | F5 team | Cutover | All | Linux/Windows | Sequential-5 | To point the traffic to AWS workloads bring the old Pool down and bring the new pool up with new hostnames and Ip address on the F5 LB. | 10 mins
12 |  | Trainz/Linux Team | Post-Cutover task | Specific | Linux | Sequential-6 | Update NFS filesystem on /etc/fstab on target instance in AWS to reflect EFS details | 10 mins
13 |  | Trianz/Monitoring Team | Post-Cutover task | All | Linux/Windows | Parallel-2 | Verify application instance health & reporting on APM & Monitoring tools | 15 mins
14 |  | Trainz/App Team | Post-Cutover task | Specific | Linux/Windows | Parallel-2 | Validatng upstream and down stream connectivity(dependent on number of upstream/downstream apps) | 15 mins
15 |  | App Team | Post-Cutover task | All | Linux/Windows | Sequential-7 | Release the server to Application team and have them Verify | 15 mins
16 |  | AD Team | Post-Cutover task | All | Linux/Windows | Sequential-8 | Remove local account (trianzadmin) on AWS instance | 10 mins
17 |  | Trainz Migration Team | Post-Cutover task | All | Linux/Windows | Sequential-9 | Validation required antivirus/backup/monitoring scripts before we get sign off from | 10 mins
18 |  | Infosec Team | Post-Cutover task | All | linux/Windows | Sequential-10 | Equnix infosec team sign off as per org security mandates | 10 mins

## Rollback Plan
# | Status | Owner(s) | Phase | Task Description | Server(s) | Start Time* | End Time* | Duration | Notes | Dependencies
Roll Back Tasks (if needed) - 45 Mins
Application Server Roll back Steps
| N/A | Trianz | Application Rollback Steps | Stop all application services on the target AWS Account. |  | Yet to Start | Yet to Start
| N/A | Trianz |  | Shutdown the AWS instances. |  | Yet to Start | Yet to Start
| N/A | HIR |  | Startup the Source servers. |  | Yet to Start | Yet to Start
| N/A | Application Team |  | Connect to the Source Servers. |  | Yet to Start | Yet to Start
| N/A | Equinix |  | Enable Source CIFS/NFS on-prem Shares |  | Yet to Start | Yet to Start
| N/A | Equinix |  | Make the DNS Change A records point back to the On-Prem IP address. |  | Yet to Start | Yet to Start
Database Server Roll back Steps
| N/A | Equinix | Database Rollback Steps | Stop all application services on the AWS target database. |  | Yet to Start | Yet to Start
| N/A | Equinix |  | Startup the Source servers. |  | Yet to Start | Yet to Start
| N/A | Application Team |  | Connect to the Source Servers. |  | Yet to Start | Yet to Start
| N/A | Equinix |  | Enable Source CIFS/NFS on-prem Shares |  | Yet to Start | Yet to Start
| N/A | Equinix |  | Make the DNS Change A records point back to the On-Prem IP address. |  | Yet to Start | Yet to Start

## LZ Details (hidden)
Server | Parameter | Value
Source SLA (As per MGL)
Storage Type ( Entry / Normal / Performance)
vSphere Cluster Name
vSphere DataStore Name
Site Affinity
VLAN ID
vSphere Network Portgroup Name
DR Protection

## End-End-Tracker
Move Group | Application Name | BU | Host Name | Source IP | OS Type | OS detatils | Environment | Discovery Status | Owner Equinix | Discovery Comments | AR Status | Pilot AR Shared to customer | AR Name | AR Comments | User R-Strategy | Online R-Strategy | LZ Status | Public / Private facing | Concierto Plan ID | Target HostName | Target IP | Migration Status(Completed /Failed) | Migration Date(dd/mm/yy) | Post Migration Status | Migration Comments | Target DNS | Cutover Date Planned | Cutover Actual | Go-Live
|  |  | SV2WNAUTOQA03 | 10.193.150.3 | Windows | Microsoft Windows Server 2016 or later (64-bit) | Quality Assurance | Success | Gopi Chand Tadiboyina (gchand) | NA | Success | NA | ASSMNT_EQUI_ACCELQ_QA_28JAN_REPORT | NA | Rehost | Rehost | Completed | Private | CM-PL-EQUI95 | AE2WNAUTOQA03 | 10.218.232.20 | Done | 2026-01-02 | TBD | NA | TBD | TBD | TBD

## Infra-Firewall-Change
Source | Destination | Protocol | Port Numbers | Time | Direction | Justification | OS
Hostname of source | Hostname of destination | Port protocol |  |  | Bi-directional/Uni-directional

## Contact List
Company | ROLE/ Description | Name | E-mail address
HiR | Application Architect
Technical Product Owner
Engineering Lead
Technical Program Manager
Porgram Sponsor
Change Management Lead
Server Specialist
Test Lead
Trianz | Program Management
Program Management
Delivery Manager
Delivery Manager
Delivery Manager
Platform Deployment Lead
Infra Architect
Infra Architect
Infra Architect
Infra Architect
D&A Lead
Application Migration delivery Lead
Application Architect
Application Architect
Application Architect
Concierto Eng. Lead
Note on A1: Specify the description of the Roles
Note on B1: Specify the description of the Roles

## Feedback tracker
# | Feedback | Raised by | Raised on | plan of Action | Action Owner | Action Status
1 | TBD

## MASTER_INFRA (hidden)
Area |  | Compute | [10 empty] | Cluster |  |  |  | Netwrok/Security | [16 empty] | Storage | [10 empty] | Database
Data Columns | Host ID | Hosted ESX version | OS Version Detail | OS Service Pack | Server Domain Name with FQDN | Server Model(DL380/BL490/Others) | Any additional HBA/PCI Cards etc (only for Physical servers) | CPU Type | CPU Clock speed | Virtual/logical CPU | Physical CPU | Memory (MB) | Does it have DR node in other DC, if yes, pls mention DR node name | Is this Server HA/Cluster with other servers(Y/N) | HA/Cluster Nodes Name | Cluster IP | Trusted/DMZ (Network Classification) | WAN accelerators | Firewall ports | Default routing, NAT | Data Privacy(Black/Gray/White) | Sub netmask | Default IP Gateway | Management IP | iLO IP | Security Zone(iNetDMZ, High security zone, Black Security Zone, Stanadard Security Zone, 3rd Party Zone) | Loadbalanced (Y/N) | If loadbalanced is Yes - LB IP | If loadbalanced is Yes. Please provide details of URL,LB policy etc.. | Internal Firewall Rules Details (Source IP,Source Zone,Port,Protocols etc..) | Soruce port | Destination port | VLAN/VRT's | OS Disk Size (GB) | Disk Mapping(C:, D: E: drives etc) | Allocated storage (GB) | Used Storage (GB) | R1-Storage | R5-Storage | R6-Storage | R1-Replicated | R5-Replicated | R6-Replicated | Storage Tier (T0,T1,T2,T3) | Database ID | DB Name | DB Description | SID or Cluster Name | App ID & Server Name using this DB | DB Version | DB Clustering details | DB Size | Database license Type (CPU/User etc..) | Rate of data change
Owner | DxC | DxC | DxC | Infosys | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | DxC | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys | Infosys
Note on N2: If the server require DR?
Note on O2: Cluster Information MSCS , VCS or Application load balancer
Note on P2: Cluster Information MSCS , VCS or Application loadbalancer
Note on AI2: OS & Data disk sizes are required to validate the no of workloads that could be migrated on a particular weekend based on the size
Note on AX2: Shared DB clusters hosting multiple applications